## Start here
Post-award control workbook — Northbridge Foundation (synthetic)
Built 28 Sep 2026 from your grant list. The figures below update automatically when you edit the Grant register and Payments sheets.
SYNTHETIC EXAMPLE — fictional organisation and data, for illustration only.
Active grants | 19
Total awarded | 235700
Paid to date | 152850
Reports overdue
Reports due in the next 30 days
Payments blocked | 8
Value of blocked payments | 58850
Payments ready for approval | 1
Grants with evidence missing or partial | 4
Grants with a due-diligence gap
Open grant conditions | 4
Data questions for you to confirm | 23
Top actions (as at 28 Sep 2026)
Issue | Priority | Grant / recipient | Next action
Payment on hold: bank details changed: Tranche 1 (£3,500): notes say bank details changed | High | CAP-10 · Eastfield Village Hall | Verify the new bank details by phone on a number you already hold before paying (owner: Priya K)
Payment on hold: bank details changed: Tranche 2 (£9,000): notes say bank details changed | High | CAP-8 · Eastfield Village Hall | Verify the new bank details by phone on a number you already hold before paying (owner: Priya K)
Paid before agreement recorded: £3,000 paid; no signed agreement on file | High | YM25/05 · St Anne's Community Choir | Obtain the signed agreement and file it (owner: Tom B)
Due diligence not recorded: £3,000 paid with no check recorded | High | HF-103 · Westside Refugee Welcome | Complete the recipient check and record the date and source (owner: Sarah J)
Due diligence not recorded: £3,000 paid with no check recorded | High | YM25/05 · St Anne's Community Choir | Complete the recipient check and record the date and source (owner: Tom B)
Payment late: Tranche 2 (£15,000) was due 10 Sep 2026; release conditions are met | High | CF-2026-002 · Lanterns Mental Health Peer Support | Approve and pay, or record why it is held (owner: Sarah J)
Condition overdue: Safeguarding policy to be provided within 3 months (by 20/09/2026) | High | YM26/02 · The Beat Box Studio CIC | Chase, or record an agreed extension (owner: Tom B)
Payment blocked: Tranche 2 (£3,600) was due 10 May 2026; waiting for interim report | High | YM25/09 · Rhythm & Roots Drumming | Chase interim report; hold payment until received (owner: Tom B)
Payment blocked: Tranche 2 (£6,250) was due 01 Sep 2026; waiting for interim report | High | YM25/03 · Northgate Music Collective | Chase interim report; hold payment until received (owner: Tom B)
Payment blocked: Tranche 1 (£1,500) due 30 Sep 2026; waiting for agreement | High | HF-102 · Mercy Street Food Bank | Chase agreement; hold payment until received (owner: Sarah J)
Where to look:
• Needs attention — every issue found, highest priority first. Tick Done as you go.
• Payments — each tranche, what releases it, and whether it is blocked or ready.
• Grant register — one row per grant; status columns recalculate from the dates you enter.
• Data questions — things in your export I could not be sure about. Please confirm.
• How to use — keeping the workbook current.

## Needs attention
Needs attention — as at 28 Sep 2026 (tick Done as you clear items)
Priority | Grant ref | Recipient | Fund | Issue | Detail | Date | Days late | £ | Owner | Next action | Done? | Your notes
High | CAP-10 | Eastfield Village Hall | Capital Grants | Payment on hold: bank details changed | Tranche 1 (£3,500): notes say bank details changed | 2026-10-15 |  | 3500 | Priya K | Verify the new bank details by phone on a number you already hold before paying | No
High | CAP-8 | Eastfield Village Hall | Capital Grants | Payment on hold: bank details changed | Tranche 2 (£9,000): notes say bank details changed | 2026-10-31 |  | 9000 | Priya K | Verify the new bank details by phone on a number you already hold before paying | No
High | YM25/05 | St Anne's Community Choir | Youth Music | Paid before agreement recorded | £3,000 paid; no signed agreement on file |  |  |  | Tom B | Obtain the signed agreement and file it | No
High | HF-103 | Westside Refugee Welcome | Hardship Fund | Due diligence not recorded | £3,000 paid with no check recorded |  |  |  | Sarah J | Complete the recipient check and record the date and source | No
High | YM25/05 | St Anne's Community Choir | Youth Music | Due diligence not recorded | £3,000 paid with no check recorded |  |  |  | Tom B | Complete the recipient check and record the date and source | No
High | CF-2026-002 | Lanterns Mental Health Peer Support | Community Fund | Payment late | Tranche 2 (£15,000) was due 10 Sep 2026; release conditions are met | 2026-09-10 | 18 | 15000 | Sarah J | Approve and pay, or record why it is held | No
High | YM26/02 | The Beat Box Studio CIC | Youth Music | Condition overdue | Safeguarding policy to be provided within 3 months (by 20/09/2026) | 2026-09-20 | 8 |  | Tom B | Chase, or record an agreed extension | No
High | YM25/09 | Rhythm & Roots Drumming | Youth Music | Payment blocked | Tranche 2 (£3,600) was due 10 May 2026; waiting for interim report | 2026-05-10 | 141 | 3600 | Tom B | Chase interim report; hold payment until received | No
High | YM25/03 | Northgate Music Collective | Youth Music | Payment blocked | Tranche 2 (£6,250) was due 01 Sep 2026; waiting for interim report | 2026-09-01 | 27 | 6250 | Tom B | Chase interim report; hold payment until received | No
High | HF-102 | Mercy Street Food Bank | Hardship Fund | Payment blocked | Tranche 1 (£1,500) due 30 Sep 2026; waiting for agreement | 2026-09-30 |  | 1500 | Sarah J | Chase agreement; hold payment until received | No
High | CAP-7 | Riverside Scout Group | Capital Grants | Payment blocked | Tranche 3 (£20,000) due 01 Oct 2026; waiting for condition | 2026-10-01 |  | 20000 | Priya K | Chase condition; hold payment until received | No
High | YM26/01 | Brass for All | Youth Music | Payment blocked | Tranche 2 (£5,000) due 01 Oct 2026; waiting for interim report | 2026-10-01 |  | 5000 | Tom B | Chase interim report; hold payment until received | No
High | CF-2025-014 | Harbour Youth Project CIO | Community Fund | Payment blocked | Tranche 2 (£10,000) due 21 Oct 2026; waiting for interim report + evidence | 2026-10-21 |  | 10000 | Sarah J | Chase interim report + evidence; hold payment until received | No
High | CF-2026-005 | Greenway Allotment Society | Community Fund | Final report overdue | Final report was due 01 Sep 2026 | 2026-09-01 | 27 |  | — | Chase the report, agree a new date or escalate | No
High | YM25/09 | Rhythm & Roots Drumming | Youth Music | Interim report overdue | Interim report was due 10 Apr 2026 | 2026-04-10 | 171 |  | Tom B | Chase the report, agree a new date or escalate | No
High | YM25/03 | Northgate Music Collective | Youth Music | Interim report overdue | Interim report was due 31 Jul 2026 | 2026-07-31 | 59 |  | Tom B | Chase the report, agree a new date or escalate | No
High | YM26/01 | Brass for All | Youth Music | Interim report overdue | Interim report was due 15 Sep 2026 | 2026-09-15 | 13 |  | Tom B | Chase the report, agree a new date or escalate | No
Medium | YM25/03 | Northgate Music Collective | Youth Music | Due diligence out of date | Last check 10 Jan 2025 (~20 months) before a further payment | 2025-01-10 |  |  | Tom B | Refresh the check before the next payment | No
Medium | CF-2025-009 | Harbour Youth Proj. | Community Fund | Final report due soon | Final report due 30 Sep 2026 (2 days) | 2026-09-30 |  |  | Sarah J | Send a reminder now | No
Medium | CF-2025-014 | Harbour Youth Project CIO | Community Fund | Interim report due soon | Interim report due 14 Oct 2026 (16 days) | 2026-10-14 |  |  | Sarah J | Send a reminder now | No
Medium |  | Friends of Castle Park |  | Awarded but not set up | approved at Sept trustees - letter not sent yet |  |  | 5000 | — | Send the award letter/agreement and create the grant record | No
Medium | CAP-7 | Riverside Scout Group | Capital Grants | Condition open | Planning permission evidence before tranche 3 |  |  |  | Priya K | Confirm when it will be met | No
Medium | CAP-7 | Riverside Scout Group | Capital Grants | Evidence partial | contractor invoices - some received |  |  |  | Priya K | Request the outstanding evidence | No
Medium | CAP-8 | Eastfield Village Hall | Capital Grants | Evidence missing | completion certificate + photos |  |  |  | Priya K | Request the outstanding evidence | No
Medium | CF-2025-009 | Harbour Youth Proj. | Community Fund | Due-diligence date unknown | Check ticked but not dated |  |  |  | Sarah J | Record when the check was done and what was checked | No
Medium | CF-2025-014 | Harbour Youth Project CIO | Community Fund | Evidence missing | receipts for tranche 1 spend - not yet |  |  |  | Sarah J | Request the outstanding evidence | No
Medium | CF-2026-005 | Greenway Allotment Society | Community Fund | Evidence missing | photos of new raised beds |  |  |  | — | Request the outstanding evidence | No
Medium | YM25/03 | Northgate Music Collective | Youth Music | Condition open | DBS checks for tutors confirmed before term 2 |  |  |  | Tom B | Confirm when it will be met | No
Low | CF-2025-022 | Northbridge Men's Shed | Community Fund | Due diligence out of date | Last check 20 Sep 2025 (~12 months) | 2025-09-20 |  |  | Tom B | Refresh before any new award | No
Low | CF-2025-021 | Oakfield Carers Network | Community Fund | Due diligence out of date | Last check 25 Sep 2025 (~12 months) | 2025-09-25 |  |  | Sarah J | Refresh before any new award | No
Low | CAP-9 | Hilltop Community Cafe | Capital Grants | Ready to close | Ended 30 Jun 2026; final report in; fully paid | 2026-06-30 |  |  | Priya K | Close the grant and file the record | No

## Payments
Grant ref | Recipient | Tranche | Amount £ | Due date | Released when | Release condition met? | Bank details check | Paid (date) | Status | Days late
CF-2025-014 | Harbour Youth Project CIO | 1 | 15000 | 2026-07-01 | Agreement | TRUE | OK | yes | Paid
CF-2025-014 | Harbour Youth Project CIO | 2 | 10000 | 2026-10-21 | Interim report + evidence | FALSE | OK |  | Blocked: waiting for interim report + evidence
CF-2025-009 | Harbour Youth Proj. | 1 | 5000 | 2025-11-03 | Agreement | TRUE | OK | yes | Paid
YM25/03 | Northgate Music Collective | 1 | 6250 | 2026-01-15 | Agreement | TRUE | OK | yes | Paid
YM25/03 | Northgate Music Collective | 2 | 6250 | 2026-09-01 | Interim report | FALSE | OK |  | Blocked: waiting for interim report | 27
YM25/05 | St Anne's Community Choir | 1 | 3000 | 2026-03-05 | Agreement | FALSE | OK | yes | Paid
CAP-7 | Riverside Scout Group | 1 | 10000 | 2026-01-12 | Agreement | TRUE | OK | yes | Paid
CAP-7 | Riverside Scout Group | 2 | 10000 | 2026-04-01 | Agreement | TRUE | OK | yes | Paid
CAP-7 | Riverside Scout Group | 3 | 20000 | 2026-10-01 | Condition | FALSE | OK |  | Blocked: waiting for condition
CAP-8 | Eastfield Village Hall | 1 | 9000 | 2026-02-20 | Agreement | TRUE | OK | yes | Paid
CAP-8 | Eastfield Village Hall | 2 | 9000 | 2026-10-31 | Evidence | FALSE | Verify |  | Blocked: verify bank details
HF-101 | Mercy Street Food Bank | 1 | 2500 | 2026-09-01 | Agreement | TRUE | OK | yes | Paid
HF-102 | Mercy Street Food Bank | 1 | 1500 | 2026-09-30 | Agreement | FALSE | OK |  | Blocked: waiting for agreement
CF-2026-002 | Lanterns Mental Health Peer Support | 1 | 15000 | 2026-02-10 | Agreement | TRUE | OK | yes | Paid
CF-2026-002 | Lanterns Mental Health Peer Support | 2 | 15000 | 2026-09-10 | Interim report | TRUE | OK |  | Ready for approval | 18
CF-2026-005 | Greenway Allotment Society | 1 | 4000 | 2026-04-03 | Agreement | TRUE | OK | yes | Paid
CF-2026-007 | Kids Code Club Northbridge | 1 | 4000 | 2026-05-01 | Agreement | TRUE | OK | yes | Paid
CF-2026-007 | Kids Code Club Northbridge | 2 | 4000 | 2026-12-01 | Interim report | FALSE | OK |  | Waiting: interim report
YM26/01 | Brass for All | 1 | 5000 | 2026-06-01 | Agreement | TRUE | OK | yes | Paid
YM26/01 | Brass for All | 2 | 5000 | 2026-10-01 | Interim report | FALSE | OK |  | Blocked: waiting for interim report
YM26/01 | Brass for All | 3 | 5000 | 2027-02-01 | Condition | FALSE | OK |  | Waiting: condition
YM26/02 | The Beat Box Studio CIC | 1 | 9500 | 2026-06-20 | Agreement | TRUE | OK | yes | Paid
CAP-9 | Hilltop Community Cafe | 1 | 11000 | 2025-12-12 | Agreement | TRUE | OK | yes | Paid
CAP-9 | Hilltop Community Cafe | 2 | 11000 | 2026-06-30 | Final report | TRUE | OK | yes | Paid
HF-103 | Westside Refugee Welcome | 1 | 3000 | 2026-09-15 | Agreement | TRUE | OK | yes | Paid
CF-2025-021 | Oakfield Carers Network | 1 | 10000 | 2025-10-01 | Agreement | TRUE | OK | yes | Paid
CF-2025-021 | Oakfield Carers Network | 2 | 10000 | 2026-04-01 | Interim report | TRUE | OK | yes | Paid
CF-2025-022 | Northbridge Men's Shed | 1 | 6000 | 2025-10-01 | Agreement | TRUE | OK | yes | Paid
YM25/09 | Rhythm & Roots Drumming | 1 | 3600 | 2025-10-10 | Agreement | TRUE | OK | yes | Paid
YM25/09 | Rhythm & Roots Drumming | 2 | 3600 | 2026-05-10 | Interim report | FALSE | OK |  | Blocked: waiting for interim report | 141
CAP-10 | Eastfield Village Hall | 1 | 3500 | 2026-10-15 | Evidence | TRUE | Verify |  | Blocked: verify bank details
Formulas:
Days late = IF(OR([Grant ref]="",[Paid (date)]<>"",[Due date]="",[Due date]>=TODAY()),"",TODAY()-[Due date])

## Grant register
Grant ref | Recipient | Reg. no. | Fund | Owner | Awarded £ | Paid to date £ | Award date | End date | Agreement signed | DD last checked | Conditions | Conditions met? | Interim report due | Interim received | Final report due | Final received | Evidence required | Evidence status | Report status | Payments | Checks | Needs attention? | Notes
CF-2025-014 | Harbour Youth Project CIO | 1181234 | Community Fund | Sarah J | 25000 | 15000 | 2026-07-01 | 2027-06-30 | yes | 2026-07-02 | Restricted to youth skills delivery | Yes | 2026-10-14 |  | 2027-07-31 |  | receipts for tranche 1 spend - not yet | Missing | Interim due in 16d | Payment blocked | Evidence missing; | Yes | chased for receipts 16/9
CF-2025-009 | Harbour Youth Proj. |  | Community Fund | Sarah J | 5000 | 5000 | 2025-11-03 | 2026-08-31 | yes | yes |  |  |  |  | 2026-09-30 |  |  |  | Final due in 2d |  | DD date unknown; | Yes
YM25/03 | Northgate Music Collective | 1190001 | Youth Music | Tom B | 12500 | 6250 | 2026-01-15 | 2026-12-31 | yes | 2025-01-10 | DBS checks for tutors confirmed before term 2 | No | 2026-07-31 |  | 2026-12-31 |  |  |  | Interim overdue 59d | Payment blocked | DD over 12 months; Condition open; | Yes | chased 2x, new coordinator started Aug
YM25/05 | St Anne's Community Choir |  | Youth Music | Tom B | 3000 | 3000 | 2026-03-05 | 2027-02-28 | [6 empty] | 2027-03-31 |  |  |  | OK |  | No DD date; No agreement; | Yes | paid before agreement returned?? check
CAP-7 | Riverside Scout Group | 1100456 | Capital Grants | Priya K | 40000 | 20000 | 2026-01-01 | 2027-03-31 | 2026-01-12 | 2025-12-12 | Planning permission evidence before tranche 3 | No | 2026-06-30 | 2026-07-02 | 2027-03-31 |  | contractor invoices - some received | Partial | OK | Payment blocked | Condition open; Evidence partial; | Yes
CAP-8 | Eastfield Village Hall | 1123456 | Capital Grants | Priya K | 18000 | 9000 | 2026-02-20 | 2026-12-31 | yes | 2026-02-18 |  |  |  |  | 2026-10-31 |  | completion certificate + photos | Missing | OK | Payment blocked | Evidence missing; | Yes | bank details changed - verify before next payment!
HF-101 | Mercy Street Food Bank | 1170777 | Hardship Fund | Sarah J | 2500 | 2500 | 2026-09-01 | 2026-12-31 | yes | 2026-08-20 |  |  |  |  | 2027-01-31 |  |  |  | OK |  |  | No
HF-102 | Mercy Street Food Bank | 1170777 | Hardship Fund | Sarah J | 1500 | 0 | 2026-09-12 | 2026-12-31 |  | 2026-08-20 |  |  |  |  | 2027-01-31 |  |  |  | OK | Payment blocked | No agreement; | Yes
CF-2026-002 | Lanterns Mental Health Peer Support | 1201122 | Community Fund | Sarah J | 30000 | 15000 | 2026-02-10 | 2027-02-09 | yes | 2026-02-01 |  |  | 2026-08-10 | 2026-08-05 | 2027-03-09 |  |  |  | OK | Payment ready |  | Yes | interim report fine - T2 to go to Oct trustees?
CF-2026-005 | Greenway Allotment Society |  | Community Fund |  | 4000 | 4000 | 2026-04-03 | 2026-08-31 | yes | 2026-04-01 |  |  |  |  | 2026-09-01 |  | photos of new raised beds | Missing | Final overdue 27d |  | Evidence missing; | Yes
CF-2026-007 | Kids Code Club Northbridge | 1195555 | Community Fund | Tom B | 8000 | 4000 | 2026-05-01 | 2027-04-30 | yes | 2026-04-28 |  |  | 2026-11-01 |  | 2027-04-30 |  |  |  | OK |  |  | No
YM26/01 | Brass for All | 1150333 | Youth Music | Tom B | 15000 | 5000 | 2026-06-01 | 2027-05-31 | yes | 2026-05-30 | Spring termly report by 15/01/2027 before the February payment | No | 2026-09-15 |  | 2027-05-31 |  |  |  | Interim overdue 13d | Payment blocked | Condition open; | Yes
YM26/02 | The Beat Box Studio CIC | CIC12345678 | Youth Music | Tom B | 9500 | 9500 | 2026-06-20 | 2027-06-30 | yes | 2026-06-18 | Safeguarding policy to be provided within 3 months (by 20/09/2026) | No |  |  | 2027-06-30 |  |  |  | OK |  | Condition open; | Yes
CAP-9 | Hilltop Community Cafe | 1188888 | Capital Grants | Priya K | 22000 | 22000 | 2025-12-12 | 2026-06-30 | yes | 2025-12-10 |  |  |  |  | 2026-06-30 | 2026-06-28 | invoices received | Received | OK |  |  | No | all done?
HF-103 | Westside Refugee Welcome | 1177777 | Hardship Fund | Sarah J | 3000 | 3000 | 2026-09-15 | 2027-03-31 | yes | [5 empty] | 2027-04-30 |  |  |  | OK |  | No DD date; | Yes | urgent award - DD to follow
CF-2025-021 | Oakfield Carers Network | 1166666 | Community Fund | Sarah J | 20000 | 20000 | 2025-10-01 | 2026-09-30 | yes | 2025-09-25 |  |  | 2026-04-01 | 2026-04-01 | 2026-10-31 |  | received with interim | Received | OK |  | DD over 12 months; | Yes
CF-2025-022 | Northbridge Men's Shed | 1160000 | Community Fund | Tom B | 6000 | 6000 | 2025-10-01 | 2026-09-30 | yes | 2025-09-20 |  |  |  |  | 2026-10-31 |  |  |  | OK |  | DD over 12 months; | Yes
YM25/09 | Rhythm & Roots Drumming |  | Youth Music | Tom B | 7200 | 3600 | 2025-10-10 | 2026-10-09 | yes | 2025-10-05 |  |  | 2026-04-10 |  | 2026-11-09 |  |  |  | Interim overdue 171d | Payment blocked |  | Yes | project paused - lead worker on leave; extension agreed?? no record
CAP-10 | Eastfield Village Hall | 1123456 | Capital Grants | Priya K | 3500 | 0 | 2026-08-15 | 2027-03-31 | yes | 2026-02-18 |  |  |  |  | 2027-03-31 |  | quote for ramp received 02/09/2026 | Received | OK | Payment blocked |  | Yes

## Data questions
Row in your file | Grant ref | Recipient | Field | Value in your file | Question | What I assumed | Your answer
3 | CF-2025-009 | Harbour Youth Proj. | dd_checked | Y | Due diligence ticked but no date recorded. When was it done? | Treated as done, date unknown
5 | YM25/05 | St Anne's Community Choir | notes | paid before agreement returned?? check | Note needs a decision or confirmation.
6 | CAP-7 | Riverside Scout Group | award_date | Jan-26 | Award date: month only ('Jan-26'); assumed 1st of month. | Used as stated
7 | CAP-8 | Eastfield Village Hall | evidence | completion certificate + photos | Evidence named but status unclear: received or still missing?
7 | CAP-8 | Eastfield Village Hall | notes | bank details changed - verify before next payment! | Note needs a decision or confirmation.
9 | HF-102 | Mercy St Foodbank | agreement_signed | pending | Agreement not yet signed? | Treated as not signed
11 | CF-2026-005 | Greenway Allotment Society | evidence | photos of new raised beds | Evidence named but status unclear: received or still missing?
11 | CF-2026-005 | Greenway Allotment Society | owner |  | No owner recorded. Who is responsible for this grant?
14 | YM26/02 | The Beat Box Studio CIC | reg_no | CIC 12345678 | Registration number is not a standard charity number. Is this a company/CIC number? | Kept as given
19 | YM25/09 | Rhythm & Roots Drumming | notes | project paused - lead worker on leave; extension agreed?? no record | Note needs a decision or confirmation.
20 |  | Friends of Castle Park | grant_ref |  | No grant reference, dates or agreement: awarded but not yet set up? | Listed as a set-up action, not as an active grant
8 | HF-101 | Mercy Street Food Bank | recipient | Mercy St Foodbank / Mercy Street Food Bank | Same organisation spelt differently? | Treated as one organisation
2 | CF-2025-014 | Harbour Youth Project CIO | recipient | Harbour Youth Proj. / Harbour Youth Project CIO | Same organisation under two names? | Kept separate until confirmed
|  |  | owner | Priya, Priya K | Owner written several ways. Same owner? | Grouped as 'Priya K'
|  |  | owner | Sarah, sarah j, Sarah J, SJ | Owner written several ways. Same owner? | Grouped as 'Sarah J'
|  |  | owner | TB, Tom, Tom B | Owner written several ways. Same owner? | Grouped as 'Tom B'
|  |  | fund | Capital, Capital Grants | Fund written several ways. Same fund? | Grouped as 'Capital Grants'
|  |  | fund | Community Fund, community fund | Fund written several ways. Same fund? | Grouped as 'Community Fund'
|  |  | fund | Hardship, Hardship Fund | Fund written several ways. Same fund? | Grouped as 'Hardship Fund'
6 | CAP-7 | Riverside Scout Group | payment_schedule | 3 x quarterly; £20,000 paid | Schedule says 3 quarterly payments and £20,000 is paid. I have assumed two £10,000 payments made and the third (£20,000) due 1 Oct once planning permission evidence is in. Are those the right amounts? | Assumed exactly that
13 | YM26/01 | Brass for All | payment_schedule | Feb after termly report | The February payment depends on the spring termly report, which has no column in your sheet. I have recorded it as a condition dated 15 Jan 2027. OK? | Tracked as a condition
|  |  | paid dates | paid to date only | Your sheet records how much has been paid but not when. Paid tranches show 'yes' instead of a date; add dates if you want them in the audit trail. | Paid = yes, date unknown
9 | HF-102 | Mercy St Foodbank | recipient | same charity no. 1170777 | HF-101 and HF-102 share charity number 1170777, so I have used one name for both. | Named Mercy Street Food Bank

## How to use
How to keep this workbook working
1. Record events as they happen: enter the date a report arrives (Grant register, 'received' columns), set Evidence status, set 'Conditions met?', and enter the date each tranche is paid (Payments, 'Paid (date)').
2. The Report status, Payments, Checks and Status columns recalculate from those dates every day. Filter 'Needs attention?' = Yes on the Grant register to see what still needs action.
3. Each tranche has a 'Released when' condition. Status shows 'Ready for approval' once that condition is met and the payment is within 30 days, and 'Blocked' if the payment is due but the condition is not met.
4. If a grantee reports new bank details, set 'Bank details check' to Verify until you have confirmed the change by phone on a number you already hold. The tranche stays blocked until you set it back to OK.
5. 'Needs attention' is the list as at the build date. Tick Done as items are cleared. Within 60 days of delivery I will refresh it once from an updated export at no extra cost.
6. This workbook organises information you supplied. It does not move money, contact grantees or give legal, audit or regulatory advice; decisions stay with you and your trustees.